## Overview
Adaptive Session-Aware Recommendation System
Four-week development plan for a 3-student IT4043E Big Data Storage and Processing project
Item | Plan value |  | Key course requirements | Evidence in this plan | Source
Planning baseline | 2026-10-22 |  | Lambda/Kappa architecture | Lambda data-flow diagram and phase gates | IT4043E course requirements
Duration | 4 weeks |  | Spark + HDFS/Parquet | Batch, windows, pivots, joins, optimization | PROJECT_CONTEXT_V2.md
Team | 3 university students |  | Kafka + Structured Streaming | Replay/live topics, watermark, state, recovery | Accessed 2026-10-22
Architecture | Lambda Architecture |  | NoSQL + serving | Cassandra tables and FastAPI endpoints | https://datalab.vn/teaching/it4043e-big-data-storage-and-processing
Primary course focus | Big Data storage, batch processing, streaming, distributed benchmarking |  | Visualization | React/Vite catalog, cart, recommendations
Primary dataset split | October = train/history; November = temporal test/replay |  | Kubernetes/cloud | Week 4 smoke deployment
Primary acceptance gates | G1 batch vertical slice; G2 streaming vertical slice; G3 evidence; G4 final rehearsal
Must-not-claim | No unqualified exactly-once or real-time-source claim
Week | Theme | Exit gate | Primary output
Week 1 | Data evidence + batch baseline | G1 | October sample to ALS candidates
Week 2 | Kafka + Structured Streaming + vertical slice | G2 | Event to session state to API
Week 3 | Adaptive ranking + evaluation + benchmarks | G3 | Quality and distributed evidence
Week 4 | Recovery + deployment + report + demo | G4 | Reproducible final package

## Task Board
Task Board
Edit Owner, Status, Priority, and Notes during weekly planning. Effort is estimated team time.
ID | Week | Workstream | Task | Owner | Effort (h) | Depends on | Deliverable / acceptance evidence | Priority | Status | Notes
P0-01 | 1 | Planning | Confirm member roles, available hardware, dataset location, and Kubernetes/cloud access | Member 1 / 2 / 3 | 2 | None | Decision log entry and assigned owners | P0 | Not Started | G1 prerequisite
P0-02 | 1 | Data | Acquire October/November data and record file sizes/checksums | Member 1 | 2 | P0-01 | docs/dataset.md source and acquisition record | P0 | Not Started
P0-03 | 1 | Data | Inspect schemas, event types, nulls, cardinalities, and row counts | Member 1 | 4 | P0-02 | Profiling output for both months | P0 | Not Started
P0-04 | 1 | Data | Measure Oct/Nov overlap and identify cold-start severity | Member 1 | 3 | P0-03 | User/product/category/brand overlap table | P0 | Not Started
P0-05 | 1 | Data | Inspect skew and select sample rows covering all event types | Member 1 | 3 | P0-03 | Sample selection notes and skew summary | P0 | Not Started
P0-06 | 1 | Architecture | Freeze canonical event schema, config keys, and timestamp contract | Member 1 / 2 / 3 | 2 | P0-03 | Schema file, .env.example, review sign-off | P0 | Not Started
W1-01 | 1 | Batch | Scaffold repository, test layout, run commands, and configuration loader | Member 3 | 3 | P0-06 | Reproducible sample command | P0 | Not Started
W1-02 | 1 | Batch | Create data/sample/ and DEV/FULL data mode | Member 1 | 4 | P0-05 | Sample data with documented provenance | P0 | Not Started
W1-03 | 1 | Storage | Load October sample/full input to HDFS Bronze | Member 1 | 4 | W1-02 | HDFS path exists and can be read | P0 | Not Started
W1-04 | 1 | Batch | Build Spark schema validation and invalid-record report | Member 1 | 5 | W1-03 | Null/type/range validation report | P0 | Not Started
W1-05 | 1 | Batch | Build Silver Parquet with date partitions and derived date fields | Member 1 | 5 | W1-04 | Partitioned Parquet and row-count reconciliation | P0 | Not Started
W1-06 | 1 | Batch | Implement windows, pivot/unpivot, custom aggregation, and multi-stage transforms | Member 1 | 7 | W1-05 | Spark job plus explainable sample outputs | P0 | Not Started
W1-07 | 1 | Batch | Build user/product/category statistics and join examples | Member 1 | 5 | W1-05 | Gold tables and join plan evidence | P0 | Not Started
W1-08 | 1 | ML | Create weighted implicit feedback and train initial MLlib ALS | Member 1 | 6 | W1-07 | ALS model and metrics on sample data | P0 | Not Started
W1-09 | 1 | ML | Generate Top-50/Top-100 candidates and baseline response | Member 1 / 3 | 5 | W1-08 | Candidate table and API/fixture response | P0 | Not Started
W1-10 | 1 | Infrastructure | Start Docker Compose services and health checks | Member 2 | 5 | P0-06 | Compose startup log and health checks | P0 | Not Started
W1-11 | 1 | Integration | Record G1 demo and fix the first vertical-slice defects | Member 1 / 2 / 3 | 5 | W1-09, W1-10 | G1 checklist passed | P0 | Not Started | Gate
W2-01 | 2 | Streaming | Create Kafka topics, producer config, and deterministic replay event IDs | Member 2 | 5 | P0-06 | replay/live/DLQ topics | P0 | Not Started
W2-02 | 2 | Streaming | Implement November replay producer with configurable rate | Member 2 | 6 | W2-01 | Replay preserves event time and exposes ingest time | P0 | Not Started
W2-03 | 2 | Streaming | Parse and validate stream records; route invalid events to DLQ | Member 2 | 6 | W2-02 | DLQ count and valid-count metrics | P0 | Not Started
W2-04 | 2 | Streaming | Add event-time windows, watermark candidates, checkpoint, and deduplication | Member 2 | 8 | W2-03 | State query and late-event evidence | P0 | Not Started
W2-05 | 2 | Streaming | Implement session feature aggregation and Cassandra state sink | Member 2 | 8 | W2-04 | Session state rows and restart-safe upsert key | P0 | Not Started
W2-06 | 2 | Serving | Implement Cassandra candidate/product/session repositories | Member 3 | 5 | W1-09, W2-05 | Repository tests and seed/read script | P0 | Not Started
W2-07 | 2 | Serving | Implement FastAPI product, event, recommendation, and health endpoints | Member 3 | 6 | W2-06 | Endpoint contract tests | P0 | Not Started
W2-08 | 2 | Frontend | Build catalog, product detail, cart, and recommendation shell | Member 3 | 8 | W2-07 | UI loads dataset-backed products | P0 | Not Started
W2-09 | 2 | Frontend | Generate event semantics for open, add, remove, and successful checkout | Member 3 | 5 | W2-08 | Browser actions emit canonical events | P0 | Not Started
W2-10 | 2 | Integration | Complete G2 replay/live → Kafka → Spark → Cassandra → API path | Member 1 / 2 / 3 | 8 | W2-05, W2-07, W2-09 | Known-user demo with timestamps | P0 | Not Started | Gate
W3-01 | 3 | ML | Implement weighted session intent and time decay | Member 2 | 5 | W2-05 | Intent scores respond to recent events | P0 | Not Started
W3-02 | 3 | Serving | Normalize ALS, intent, popularity, and brand scores | Member 3 | 4 | W3-01 | Normalization tests and bounded scores | P0 | Not Started
W3-03 | 3 | Serving | Implement weighted re-ranking with configurable parameters | Member 3 | 5 | W3-02 | Top-K changes after dominant session category | P0 | Not Started
W3-04 | 3 | Serving | Implement known-user, new-user-with-clicks, and global-popularity cold-start paths | Member 3 | 5 | W3-03 | API never fails for unknown user | P0 | Not Started
W3-05 | 3 | Evaluation | Implement temporal Popularity vs ALS vs adaptive evaluation | Member 1 | 7 | W1-08, W3-03 | NDCG@10 and HitRate@10 tables | P0 | Not Started
W3-06 | 3 | Evaluation | Implement Time-to-Adapt and Purchase HitRate@10 where supported | Member 1 | 5 | W3-05 | Adaptation result table and limitations | P1 | Not Started
W3-07 | 3 | Benchmark | Compare CSV, Parquet, and partition pruning | Member 1 | 5 | W1-05 | Runtime/bytes-read comparison | P0 | Not Started
W3-08 | 3 | Benchmark | Compare broadcast vs sort-merge, caching, and AQE/skew handling | Member 1 / 2 | 8 | W1-07 | Explain plans and measured comparison | P0 | Not Started
W3-09 | 3 | Benchmark | Run replay throughput, Kafka lag, and P50/P95/P99 streaming latency | Member 2 | 7 | W2-02, W2-04 | Rate/lag/latency table and saturation point | P0 | Not Started
W3-10 | 3 | Benchmark | Run 1/2/4 executor scaling with fixed workload | Member 2 | 5 | W3-09 | Speedup/efficiency table | P1 | Not Started
W3-11 | 3 | Documentation | Draft architecture, data, benchmark, and reproducibility docs | Member 1 / 2 / 3 | 6 | W3-05, W3-09 | Docs match implementation and evidence paths | P0 | Not Started
W3-12 | 3 | Integration | Record G3 demo and freeze benchmark configurations | Member 1 / 2 / 3 | 4 | W3-03, W3-09 | G3 checklist and config snapshot | P0 | Not Started | Gate
W4-01 | 4 | Monitoring | Add Prometheus metrics and core Grafana panels | Member 3 | 6 | W3-09 | Input rate, processing rate, lag, latency panels | P1 | Not Started
W4-02 | 4 | Reliability | Execute kill/restart from checkpoint and inspect duplicate/loss behavior | Member 2 | 6 | W2-04, W2-05 | Recovery report with measured results | P0 | Not Started
W4-03 | 4 | Deployment | Harden Compose startup, health checks, and one-command sample run | Member 2 / 3 | 5 | W4-01 | Clean-environment run succeeds | P0 | Not Started
W4-04 | 4 | Deployment | Deploy minimum stack to Kubernetes or approved cloud equivalent | Member 2 | 8 | W4-03 | Manifest/runbook and smoke evidence | P0 | Not Started
W4-05 | 4 | QA | Run unit, integration, schema, API, and UI smoke tests | Member 1 / 2 / 3 | 6 | W4-02, W4-03 | Test report and limitations | P0 | Not Started
W4-06 | 4 | Reproducibility | Execute full reproduction rehearsal from sample data | Member 1 / 2 / 3 | 6 | W4-05 | Reproduction log with elapsed times | P0 | Not Started
W4-07 | 4 | Report | Finalize problem, architecture, implementation, lessons learned, limitations | Member 1 / 2 / 3 | 8 | W4-06 | Report draft tied to evidence | P0 | Not Started
W4-08 | 4 | Demo | Freeze demo persona/data, script, screenshots, and fallback recording | Member 3 | 5 | W4-06 | 8–10 minute demo script and backup | P0 | Not Started
W4-09 | 4 | Presentation | Rehearse technical questions and benchmark explanation | Member 1 / 2 / 3 | 4 | W4-07, W4-08 | Timed rehearsal and Q&A notes | P0 | Not Started
W4-10 | 4 | Acceptance | Run G4 checklist and archive code, config, results, and docs | Member 1 / 2 / 3 | 4 | W4-07, W4-08, W4-09 | Final acceptance record | P0 | Not Started | Gate

## Weekly Schedule
Weekly Schedule and Gates
Use this view for stand-ups and Friday gate reviews. Parallel work is intentional, but integration gates are shared.
Week | Day | Member 1 | Member 2 | Member 3 | Shared gate / integration | Evidence to archive | Status
1 | Day 1 | Dataset acquisition + schema | Role setup + Compose check | Repo scaffold + config | Confirm inputs and owners | Checksums, decision log | Not Started
1 | Day 2 | Profiling + overlap | Kafka/infra feasibility | API contract draft | Freeze event schema | Profiling report | Not Started
1 | Day 3 | HDFS Bronze + validation | Compose services | Sample UI shell | Sample data usable | HDFS path + sample data | Not Started
1 | Day 4 | Silver + aggregates | Kafka topic plan | Static serving fixture | Batch outputs reconcile | Spark outputs + explain plan | Not Started
1 | Day 5 | ALS + candidates | Health checks | Baseline response | G1: offline vertical slice | G1 checklist | Not Started
2 | Day 6 | Batch fixes | Replay producer | Cassandra repository | Replay produces valid events | Kafka offsets | Not Started
2 | Day 7 | Batch docs | Validation + DLQ | FastAPI endpoints | Invalid records visible | DLQ counts | Not Started
2 | Day 8 | Candidate read path | Watermark + state | Frontend catalog | State is queryable | Streaming progress | Not Started
2 | Day 9 | Evaluation fixture | Cassandra sink | Event semantics + cart | One browser action reaches state | API/UI logs | Not Started
2 | Day 10 | Batch/ML support | Streaming fixes | UI integration | G2: end-to-end event path | G2 video/screenshots | Not Started
3 | Day 11 | Quality eval | Session intent | Normalization/re-ranking | Intent shifts after events | Intent comparison | Not Started
3 | Day 12 | NDCG/HitRate | Watermark experiments | Cold-start branches | Known/new user behavior | Metric table | Not Started
3 | Day 13 | Time-to-Adapt | Load harness | Demo updates | Adaptation claim measurable | Adaptation table | Not Started
3 | Day 14 | Storage/join/cache | Throughput/lag/latency | Docs + diagrams | Benchmarks are controlled | Raw benchmark outputs | Not Started
3 | Day 15 | Benchmark interpretation | Scaling | G3 rehearsal | G3: evidence frozen | G3 checklist | Not Started
4 | Day 16 | Report methods | Recovery test prep | Monitoring panels | Metrics visible | Dashboard screenshot | Not Started
4 | Day 17 | Report results | Kill/restart + recovery | Compose hardening | Recovery results documented | Recovery report | Not Started
4 | Day 18 | Final evaluation | Kubernetes/cloud smoke | Demo fallback recording | Deployment health passes | Manifest + runbook | Not Started
4 | Day 19 | Final report edit | Clean-environment run | Demo/presentation | All known gaps explicit | Reproduction log | Not Started
4 | Day 20 | Final report and slides | Archive artifacts | Final demo rehearsal | G4: final acceptance | Final package | Not Started

## Requirements
Course Requirement Traceability
Each row must have implementation evidence before the final report is considered complete.
ID | Area | Course requirement | Implementation response | Evidence to save | Planned week | Priority | Status
R01 | Architecture | Lambda or Kappa architecture | Lambda: October batch + November/live speed layer + serving layer | Architecture diagram and data-flow explanation | Weeks 1–4 | P0 | Open
R02 | Pipeline | End-to-end ingestion → processing → storage → visualization | HDFS → Spark → Kafka/Streaming → Cassandra → FastAPI → React | G2/G4 logs and screenshots | Weeks 2–4 | P0 | Open
R03 | Compute | Apache Spark | PySpark batch and Structured Streaming | Source, Spark UI, explain plans | Weeks 1–4 | P0 | Open
R04 | Storage | HDFS or equivalent | HDFS Bronze and date-partitioned Parquet Silver | Paths, row counts, file layout | Week 1 | P0 | Open
R05 | Queue | Kafka/RabbitMQ/etc. | Kafka replay, live, and DLQ topics | Topic config, offsets, lag | Weeks 2–3 | P0 | Open
R06 | NoSQL | NoSQL database | Cassandra serving and state tables | Schema and read/write tests | Week 2 | P0 | Open
R07 | Deployment | Kubernetes or cloud | Minimum smoke deployment late in Week 4 | Manifest/runbook/health output | Week 4 | P0 | Open
R08 | Spark skills | Complex aggregations | Windows, pivots, custom aggregation | Sample output and code reference | Week 1 | P0 | Open
R09 | Spark skills | Advanced transformations | Multi-stage transforms and native functions | Explain plan and tests | Week 1 | P0 | Open
R10 | Spark skills | Join operations | Broadcast and sort-merge comparison | Runtime and shuffle evidence | Weeks 1 and 3 | P0 | Open
R11 | Spark skills | Performance optimization | Partition pruning, cache/persist, AQE/skew | Benchmark table | Week 3 | P0 | Open
R12 | Streaming | Structured Streaming | Output modes, checkpoint, stateful query | Query progress and checkpoint | Weeks 2–4 | P0 | Open
R13 | Streaming | Watermarking and late data | 2/5/10-minute comparison where feasible | Accepted/dropped late counts | Weeks 2–3 | P0 | Open
R14 | Streaming | State management and exactly-once discussion | Bounded session state, dedup, restart measurement | Recovery report and explicit limitation | Weeks 2 and 4 | P0 | Open
R15 | Report | Problem, architecture, implementation, lessons learned | Final report tied to evidence | Report and diagrams | Week 4 | P0 | Open

## Benchmarks
Benchmark Plan
Change one controlled factor at a time. Save raw output, environment, command, and configuration with each run.
ID | Family | Question / comparison | Fixed setup | Controlled factor | Metrics | Success evidence | Owner | Week | Status
B01 | Recommendation quality | Popularity vs ALS vs adaptive reranking | October train, November temporal test | method | NDCG@10, HitRate@10 | Adaptive approach is compared under same split | M1 | 3 | Not Started
B02 | Adaptation | Static ALS vs session-aware | Replay a dominant category sequence | number of new events | Time-to-Adapt | Session-aware path changes Top-K earlier | M1 | 3 | Not Started
B03 | Storage | CSV vs Parquet vs partitioned Parquet | Same date-filtered query | format | runtime, bytes read, scan size | Explain partition benefit | M1 | 3 | Not Started
B04 | Join | Broadcast vs sort-merge | Same join and input snapshot | join strategy | runtime, shuffle, max task | Explain appropriate use | M1/M2 | 3 | Not Started
B05 | Optimization | No cache vs cache/persist | Repeated reused DataFrame | cache mode | runtime, memory | Cache only reused data | M1 | 3 | Not Started
B06 | Optimization | Default vs AQE/skew | Same skewed input | AQE setting | max/median task, spill | Record whether skew matters | M2 | 3 | Not Started
B07 | Streaming load | Replay rate sweep | 1k to 10k events/s; higher if stable | input rate | processing rate, lag, P50/P95/P99 | Identify sustainable rate | M2 | 3 | Not Started
B08 | Scaling | 1/2/4 executors | Fixed workload | executor count | throughput, P95, speedup, efficiency | Explain diminishing returns | M2 | 3 | Not Started
B09 | Watermark | 2/5/10 minutes | Same late-event fixture | watermark | late accepted/dropped, state, latency | Select default with trade-off | M2 | 3 | Not Started
B10 | Recovery | Kill and restart from checkpoint | Known event set | failure point | recovery time, loss, duplicates, lag | Document exactly-once limits | M2 | 4 | Not Started

## Risks & Decisions
Risks, Rescue Actions, and Open Decisions
Resolve high-impact items early. The plan can proceed with conservative defaults if no answer arrives.
ID | Risk | Probability | Impact | Trigger / failure mode | Rescue action | Decision due | Owner | Status
K01 | Full dataset too large for hardware | High | High | Sample succeeds but full run exceeds disk/RAM/time | Use sample for development; selected full-data runs only; report limits | Before Week 2 | M1 | Open
K02 | No Kubernetes/cloud access | Medium | High | No deployment evidence by Week 4 | Use Minikube/kind if available; otherwise approved cloud-equivalent | End of Week 2 | M2 | Open
K03 | Spark/Cassandra sink instability | Medium | High | G2 blocked by sink retries/schema mismatch | Use deterministic upserts and narrow tables; keep a fixture sink for debugging | First sink test | M2 | Open
K04 | Streaming state growth | Medium | High | Memory/state rows grow with replay | Bound windows, compare watermarks, measure state size | First load run | M2 | Open
K05 | Benchmarks are not reproducible | Medium | Medium | Same script gives different workload/metrics | Freeze config, seed replay, record machine/runtime and raw outputs | Before Week 3 benchmarks | All | Open
K06 | UI consumes too much time | High | Medium | Frontend backlog after Week 2 | Keep catalog/detail/cart/recommendations only; cut polish | Week 2 gate | M3 | Open
K07 | Low Oct/Nov overlap | Medium | High | ALS coverage is weak on November users/products | Measure overlap early and use category/global popularity fallback | Week 1 profiling | M1 | Open
K08 | Late interface changes | Medium | High | Event/API/Cassandra contracts change after G2 | Freeze contracts and hold daily integration check | Day 10 | All | Open
K09 | Exactly-once claim challenged | Medium | High | Restart produces duplicates or Cassandra is not transactional | Use at-least-once wording with idempotent upserts and evidence | Recovery test | M2 | Open
Open questions
ID | Question | Why it matters | Related task | Status
Q01 | Member names and skill levels | Affects role assignment and peer review | P0-01 | Open
Q02 | Dataset already downloaded? | Affects Week 1 acquisition estimate | P0-02 | Open
Q03 | Hardware RAM/CPU/disk | Affects full-data and scaling benchmark scope | P0-01 | Open
Q04 | Kubernetes/kind/cloud access | Affects Week 4 deployment route | P0-01 | Open
Q05 | Final submission date and contribution evidence | Affects report and rehearsal buffer | P0-01 | Open
Q06 | Exact grading rubric beyond course page | Affects evidence priority | P0-01 | Open
Q07 | Allowed external services/cloud | Affects deployment and monitoring | P0-01 | Open